## Dashboard Summary
Summary of Test Results To Date
Total System Test Cases |  | QA Server | Staging Server | Production Server | Totals | Summary
Defined |  | 15 | 0 | 0 | 15 | This Summary is not completed yet, not all relevant tests are written and executed and reported yet. However the QA tried to make sure that all efforts will be recorded and summarized properly.
Not Defined |  | 9 | 23 | 23 | 9
Executed |  | 7 | 0 | 0 | 7
Passed |  | 5 | 0 | 0 | 5
Failed |  | 2 | 0 | 0 | 2
Deferred |  | 0 | 0 | 0 | 0
Blocked |  | 6 | 0 | 0 | 6
NOT resolved |  | 2 | 0 | 0 | 2
% test cases executed |  | 46.67% | 0% | 0%
% successful (of defined) |  | 33.33% | 0% | 0%
% successful (of executed) |  | 71.43% | 0% | 0%
% deferred (of defined) |  | 0% | 0% | 0%
Requirement Coverage
Priority | Covered | Not Covered | Total
5 | 3 | 2 | 5
4 | 1 | 0 | 1
3 | 1 | 2 | 3
2 | 0 | 0 | 0
1 | 0 | 0 | 0
None | 0 | 14 | 14
Totals | 5 | 18 | 23
Chart Values
Covered | Not Covered
5 | 18
Note on F4: This value is the number of Scope/Requirement IDs that do not have a test written (regardless of tier). --shunter Wednesday, July 01, 2009 12:49:35 PM
Note on A17: To be considered "Covered," it must have a Purpose, Procedure, and Expected Result

## Master Information
Test Case Master Information
General Information
Product: | QA Fundamentals Exam 26/03/2017
Release: | 1.0.0
Test Area: | QA Fundamentals Exam
Test Case Owner: | Anna Mladenova
Start Date: | 2017-03-26
Reference Documents:
System Test Platform Information
Primary Platform: | QA Server
Second Platform: | Staging Server
Third Platform: | Production Server

## Test Cases
Test case for: QA Fundamentals Exam v1.0.0 | [10 empty] | QA Server | [7 empty] | Staging Server | [7 empty] | Production Server
Scope ID | Test ID | Short Desc of Requirement | Category/Module (use for sorting purposes) | Priority | Requirement ID | Purpose | PreRequisite | Procedure | Expected Results | asdf | System test Required | System test Passed | GForge Ref ID | Actual Result | Execution Dates | Last Build Tested | All steps were executed by | asdf | System test Required | System test Passed | GForge Ref ID | Actual Results | Execution Dates | Last Build Tested | All steps were executed by | asdf | System test Required | System test Passed | GForge Ref ID | Actual Results | Execution Dates | Last Build Tested | All steps were executed by | asdf
2.2.Vocabulary | Test 2.2.1.0 | A product page is the main information block regarding a product | Vocabulary | 5 | 2.2.1. Product page | Product name visible | unregistered user | 1.Go to http://store.demoqa.com 2.Click on Product Category 3. Choose a product 4. Assert : There is a Product Name in the middle | Assert : There is a Product Name in the middle |  | Y | P | N/A | As Expected | 2017-03-26 |  | Anna Mladenova
2.2.Vocabulary | Test 2.2.1.1 |  | Vocabulary | 3 | 2.2.1. Product page | Like and Add to chart buttons available |  | 1.Go to http://store.demoqa.com 2.Click on Product Category 3. Choose a product 4. Assert :Like and Add to chart buttons available | Assert :Like and Add to chart buttons available |  | Y | P |  | As Expected | 2017-03-26 |  | Anna Mladenova
2.2.Vocabulary | Test 2.2.1.2 |  | Vocabulary | 5 | 2.2.1. Product page | Product price in USD, also if discount is available |  | 1.Go to 2.Click on Product Category 3. Choose a product 4.Assert:Product price in USD, also if discount is available | Assert:Product price in USD, also if discount is available |  | Y | P |  | As Expected | 2017-03-26 |  | Anna Mladenova
2.2.Vocabulary | Test 2.2.1.3 |  | Vocabulary | 5 | 2.2.1. Product page | “People who bought this item also bought” section available |  | 1.Go to http://store.demoqa.com 2.Click on Product Category 3. Choose a product 4. Assert :“People who bought this item also bought” section available | Assert :“People who bought this item also bought” section available |  | Y | B |  | There is a section as expected but some of the product pictures not visible. Issue "bug" opened and assigned to DevLead | 2017-03-26
2.2.Vocabulary | [10 empty] | Y
2.2.Vocabulary |  |  | Vocabulary |  | 2.2.2. Simple view | [5 empty] | Y |  | N/A |  | 2017-03-26 |  | Anna Mladenova
2.2.Vocabulary |  |  | Vocabulary |  | 2.2.3. Latest products view | [5 empty] | Y |  | N/A |  | 2017-03-26 |  | Anna Mladenova
[11 empty] | Y |  | N/A |  | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification |  | Loads header, navigation bar and a home page | Use case 1 |  | 2.3.1.0 | [5 empty] | Y | P | N/A |  | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification | Test 2.3.2.0 | Navigation bar | Use case 2 | 4 | 2.3.2.0 | The navigation bar has navigational hyperlinks to the Home, Product category, Services & Support, All Products. Also-navigation to the Checkout and My Account pages |  | 1.Go to http://store.demoqa.com 2.Check Navigation bar 3. Assert :All expected sections available | All relevant sections to be available and named correctly |  | Y | F | N/A | No "Services and Support" Section available/visible! #0(no title instead) | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification | Test 2.3.2.1 | Navigation bar – Checkout | Use case 2 | 3 | 2.3.2.1 | Register page should be present for unregistered users! |  | 1.Go to http://store.demoqa.com 2.Click on "My Account" 4.Assert: There shoud be Register button/section available |  |  | Y | P |  |  | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification | Test 2.3.2.2 | Navigation bar – user management | Use case 2 | 5 | 2.3.2.2 | My account hyperlink navigating to the Log in and Register page should be present for unregistered user |  | 1.Go to http://store.demoqa.com 2.Click on "My Account" 4.Assert: There shoud be Register button/section available |  |  | Y | F |  | Deffered due to unavailability to create valid registerred user account | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification | Test 2.3.2.2.1 | Navigation bar – user management | Use case 2 | 5 | 2.3.2.2 | Hyperlinks to the My account page and to Logout page should be present for registered user |  |  |  |  | Y | B |  | Blocked due to unavailability to register. "ERROR: You are not allowed to register because your IP address is currently locked!" Error message thrown when submitting valid credentials. | 2017-03-26
2.3.Functional requirement specification | Test 2.3.2.2.2 | Navigation bar – user management | Use case 2 | 3 | 2.3.2.2 | When registered user is successfully logged out, there should be a redirect to the Log in and Register page. |  |  |  |  | Y | B |  | Blocked due to unavailability to register. "ERROR: You are not allowed to register because your IP address is currently locked!" Error message thrown when submitting valid credentials | 2017-03-26
2.3.Functional requirement specification | Test 2.3.3.0 | Home page | Use case 3 |  | 2.3.3.0 | [9 empty] | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification |  | Products Category Page | Use case 4 |  | 2.3.4.0 | [9 empty] | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification |  | Services & Support | Use case 5 |  | 2.3.5.0 | [9 empty] | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification |  | Add product to cart | Use case 6 |  | 2.3.6.0 | [6 empty] | B |  |  | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification |  | All products | Use case 7 |  | 2.3.7.0 | [6 empty] | B |  |  | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification
2.3.Functional requirement specification |  | My account | Use case 8 |  | 2.3.8.0 | [5 empty] | Y | B |  | Blocked due to unavailability to register. "ERROR: You are not allowed to register because your IP address is currently locked!" Error message thrown when submitting valid credentials | 2017-03-26 |  | Anna Mladenova
2.3.Functional requirement specification |  | My account-Purchase Hystory | Use case 8 |  | 2.3.8.1
2.3.Functional requirement specification |  | My account-Your Details | Use case 8 |  | 2.3.8.2
2.3.Functional requirement specification |  | Search | Use case 9 |  | 2.3.9.0

## Document History and Approval
Document History and Approval
Record milestone changes and approval to this document including: * Submission to DEV * DEV Suggested Revisions * QA modification from DEV recommendations * DEV Approval * Test Execution Complete - submitted to PM and QA Manager * Review of document * QA Manager Approval
Modified/Approved By | Date | Team/Role | Notes/Approval
Anna Mladenova | 26.03.2017 | QA | Completed work, submitted to DEV
Kevin Scott | 26.03.2017 | DEV | N/A
Kevin Lynch | 26.03.2017 | Designer | Blocked by GitHub cannot participate
Rob High | 26.03.2017 | PM | N/A

## Test Environment
Test Environment
QA Server
OS: | Development tier - Solaris (Unix)
Application Server: | N/A
Database: | N/A
Java Technologies:
Web Browser: | Microsoft Edge 38.14393.0.0, Firefox 52.0.1,Chrome
Other
Staging Server
OS: | Windows 10
Application Server: | N/A
Database: | N/A
Java Technologies:
Web Browser: | Microsoft Edge 38.14393.0.0, Firefox 52.0.1,Chrome
Other
Production Server
OS: | Windows 10
Application Server: | N/A
Database: | N/A
Java Technologies:
Web Browser: | Microsoft Edge 38.14393.0.0, Firefox 52.0.1,Chrome
Other